## Sheet1
Zone | Area Command | Project Description | Location | No of Building | Contractor | Category (Residential/Administrative) | Construction/Supply Cost | Construction/Supply Date | Renovation/Rehabilitation Cost | Renovation/Rehabilitation Date | Status | Remark
Zone A | Ogun I | Contract for the Supply and Installation of 300 Nos Solar Street Light | Senior and Junior Barracks, Sentry, Border, Imeko outstation, Ohumbe outstation, Ijoun outstation and Ijofin outstation | - | Messrs Plum Bloom Limited |  | 205950500.76 | 2026-04-02
Zone A | Ogun I | Contract for the Supply and Installation of 20 Nos Solar Street Light | Clinic, Idiroko | - | Messrs JRB Solar Investment Ltd |  | 1044283380 | 2025-07-18
Zone A | Ogun I | Contract for the construction of Drainage and Landscaping at Senior & Junior officers Barracks | Idiroko | - | Messrs Almabil intergrated Services Limited |  | 337497386.22
Zone A | Ogun I | Contract for the Renovation of 1 No 30 Man rank and file to 1 No 33 1 bedroom flats and renovation of 30 Man rank and file with external works (Block C & D) at Junior arracks | Idiroko |  | Messrs Standard Connections Ltd. | Residential |  |  | 1239607295.23
Zone A | Ogun I | 2 Nos 5 Bedrooms Flat | Obele Border | 2 |  | Residential | [5 empty] | Abandoned
Zone A | Ogun I | 2 Nos 16-Man Rank and File | Ohumbe | 2 |  | Residential | [5 empty] | Abandoned
Zone A | Ogun II | Construction of 1 Block of 6 Units 2-Bedroom Terrace | Abeokuta | 6 | Messrs Ocheche Global Services | Residential | 421604152.41 | Apr, 2025 | - | - |  | Abandoned at DPC level. The contractor should be written or invited to investigate the reason for abandonement
Zone A | Ogun II | Construction of Drainage System & Landscaping | Abeokuta |  | BP Sany Co. Nig. Ltd | - | 382099362.77 | Mar, 2026 | - | -
Zone A | Ondo/Ekiti | Drilling of 2 Nos Solar Boreholes and Overhead Tank | Ekiti Outstation and Shagari Estate, Akure |  | Messrs Cheeryna Engineering Service Nig. Ltd | [6 empty] | Project is abandoned
Zone A | Oyo/Osun | The Renovation of CAC's Residence 4-Bedroom with 2-Rooms BQ Including Landscaping at Ijokodo, Ibadan Oyo State Zone A | Ijokodo, Ibadan Oyo State. | 2 | MESSRS TIME BUILDING & CONSTRUCTION COMPANY LTD | Residential |  |  |  | 2024-02-20 |  | THE PROGRESS OF WORK IS EXTREMELY SLOW
Zone A | Oyo/Osun | Contract for The Renovation of Customs House, Ikolaba GRA, Ibadan, Oyo State | Ikolaba Gra, Ibadan, Oyo State | 1 | MESSRS MEGA ULTIMATE LIMITED | Administrative |  |  | 497029169.7 | 15 May, 2024 |  | THE PROGRESS OF WORK IS EXTREMELY SLOW. REMOVAL OF OLD LIFT AND INSTALLATION OF ALUCO BOND PROFILE HAS COMMENCED
Zone A | Oyo/Osun | Drilling of 89 units of Borehole and Construction of 5000 Gallons GRP Overhead Tank with Solar System at Various Locations by the Nigeria Customs Service (2no Ijokodo Barracks, 1no Osogbo Outstation, 1no Kisi Outstation, & 1no Saki Outstation) | Ijokodo Barracks, Osogbo Outstation, Kisi Outstation, Saki Outstation. |  | MESSRS CHEERYNA ENGINEERING SERVICE NIG. LTD |  | 1735294309.88 | 10 Oct, 2023 |  |  |  | SITE ABANDONED
Zone A | Oyo/Osun | Construction of 1 No 16 Man Rank and File at Osogbo, Osun State | Osogbo, Osun State | 1 | MESSRS FREEDOM PRODUCTS INT'L LTD | Residential | 281497766.04 | 2022-07-05 |  |  |  | SITE HAS BEEN ABANDONED
Zone A | Oyo/Osun | The Drilling of Borehole and Installation of Overhead Water Tank at Okerete Outstation, Oyo State. | Okerete Outstation, Oyo State. |  | MESSRS DEEN ANALYTICS LIMITED |  | 68671602.09 | 2026-01-12 |  |  |  | WORK COMMENCED ON 28 JAN 26
Zone A | Oyo/Osun | The Construction of Perimeter Fence and Gate House at Customs Outstation, Eruwa, Oyo State | Eruwa, Oyo State |  | MESSRS RAHZA TECHNOLOGY LIMITED |  | 186349036.76 | 2026-01-12 |  |  |  | WORK COMMENCED ON 26 JAN 26
Zone A | Oyo/Osun | The Construction of Perimeter Fence and Gate House at Customs Outstation, Saki, Oyo State | Saki, Oyo State |  | MESSRS LOCOMOTIVE GLOBAL SYNERGY LIMITED |  | 392992318.96 | 2026-01-12 |  |  |  | WORK COMMENCED ON 28 JAN 26
Zone A | Oyo/Osun | The Completion of Perimeter Fence at Customs Land Okerete, Oyo State | Okerete, Oyo State |  | MESRS VOLTS SOLUTIONS LIMITED |  | 294295983.74 | 2026-01-12 |  |  | Yes | WORK COMMENCED ON 23 JAN 26
Zone A | Oyo/Osun | The Construction of Perimeter Fence for NCS Land at Igbeti, Oyo State. | Igbeti, Oyo State |  | MESSRS LATRONICS ENGINEERING LIMITED |  | 499560915.05 | 2026-01-12 |  |  | Yes | WORK COMMENCED ON 24 JAN 26
Zone A | Oyo/Osun | The Renoation of Mini Office and 6 Rooms Staff Quarters Agbororo (Revised Igbokoko) Border Station, Oyo State | Agbororo (Revised Igbokoko) Border Station, Oyo State | 2 | MESSRS LES EXECUTEURS RAPIDES LIMITED | Administrative & Residential |  |  | 220614928.39 | 2026-01-12 |  | WORK COMMENCED ON 03 FEB 26
Zone A | Oyo/Osun | The Renovation of Mini Office and 6 Rooms Staff Quarters Ayegun Border Station, Oyo State | Ayegun Border Station, Oyo State | 2 | MESSRS BIMLOYE NIGERIA LIMITED | Administrative & Residential |  |  | 219255053.39 | 2026-01-12 | Yes | WORK COMMENCED ON 23JAN 26
Zone A | Oyo/Osun | The Construction of Perimeter Fence and Construction of 2nos Gate House at Customs Centre Modakeke, Osun State. | Modakeke, Osun State | 2 | MESSRS MALMAG NIGERIA LIMITED | Administrative | 1497761333.57 | 2026-01-28 |  |  |  | -
Zone A | Oyo/Osun | The Rehabilitation of Health Center at Modakeke, Osun State (CSR) | Modakeke, Osun State | 1 | MESSRS DIGMA INTEGRATED SERVICES LIMITED | Administrative |  |  | 147150259.87 | 2026-02-05 |  | WORK COMMENCED ON 18 Feb 26
Zone A | Oyo/Osun | The Drilling of Borehole and Installation of Overhead Water Tank at Modakeke Osun State | Modakeke Osun State |  | MESSRS AMEC CONSULT LIMITED |  |  | 2026-03-02 |  |  |  | -
Zone A | Oyo/Osun | The Renovation of 3nos 30 Man Rank and File Ensuite (One Bedroom Flat) at Ijokodo Barracks, Ibadan, Oyo State | Ibadan, Oyo State | 3 | MESSRS Y DOT RESOURCES & INVESTMENT LIMITED | Residential |  |  | 943271580.79 | 2026-02-04 |  | WORK COMMENCED ON MAR 26
Zone A | Oyo/Osun | Contract for the Construction of Nigeria Customs Service ICT Training Centre, Modakeke, Osun State |  | 1 | MESSRS WHYKAY GLOBAL SERVICES | Administrative | 3632869087.49 | 2026-04-07
Zone A | Seme | Contract for the Construction of 6 Blocks of 4-Unit Bedroom Terrace for ASC'S Quarters at Seme | SEME | 6 | MESSRS WHYKAY GLOBAL SERVICES | Residential | 1740047615.45 |  | - | - | - | Work is ongoing on-site
Zone A | Seme | Contract for the Construction of 5-Blocks of 4-Units 2-Bedroom Terrace for CSC'S and SC'S at Customs Barracks, Seme Badagry, Lagos State | SEME | 5 | MESSRS OTTMAN CONSTRUCTION | Residential | 1464672490.31 | 2024-06-27 | - | - | - | 4 blocks = Ground floor block ongoing 1 block = Raft beam level (substructure) However, contractor is not on site
Zone A | Seme | Contract for the Construction of Road Network, Drainages and Landscaping of the Proposed Newly Constructed Barracks at Seme Badagry | SEME |  | MESSRS VISIBLE CONSTRUCTION LTD | - | 922909784.54 | 2024-06-27 | - | - | - | Contractor not on site. He should be written or invited to investigate the reason for not being on site
Zone A | Seme | Contract for the Demolition of Existing Dilapidated Structures and Re-Construction of Standard Office Annex II at Seme , Badagry, Lagos State | SEME |  | MESSRS TREFOREST GLOBAL SERVICES LTD | Administrative | 889948622.34 | 2025-05-21 | - | - | -
Zone A | Seme | Contract For The Completion Of The Construction Of 30 Man Rank And File At Badagry, Lagos State. | SEME |  | MESSRS PLANS GLOBAL SERVICES LIMITED | Residential | 512227664.67 | 2026-03-29 | - | - | - | Work is currently ongoing on site
Zone A | Seme | Contract For The Completion Of The Construction Of 32 Man Rank And File At Seme . | SEME |  | MESSRS ABDUL AHMED ENTERPRISE LIMITED | Residential | 741083149.01 | 2026-03-31 | - | - | - | Work is currently ongoing on site
Zone A | Seme | Contract For The Completion Of The Construction Of 2 NOS 16 Man Rank And File At Seme Badagry. | SEME | 2 | MESSRS GALIFORDTRY NIGERIA LIMITED | Residential | 683420967.32 | 2026-01-29 | - | - | - | Work is currently ongoing on site but are behind schedule
Zone A | Seme | Contract for the Renovation of 6 - Blocks, 5-Units of 1 Bedroom Flat at Senior Officers' Quarters, Seme | SEME | 6 | MESSRS ALGEBRAIC AND INDICES | Residential | - | - | 491248118.37 | 2024-03-27 | - | Work is currently on 2 blocks
Zone A | Seme | Contract for the Construction of Retaining Wall, Gate and Gate House at Babapupa Barracks, Badagry, Lagos State | SEME |  | MESSRS SAIL THROUGH CONSTRUCTION LTD | - |  |  | - | - | -
Zone A | Seme | Contract for the Construction of 2 Nos 16 Man Rank & File at Seme, Badagry (Lot A & B) | SEME | 2 | MESSRS XENON CONSTRUCTION LIMITED | Residential |  | 2022-07-08 | - | - | - | Abandoned. The contractor should be written or invited to investigate the reason for not being on site
Zone A | Seme | Contract for the Construction of 2 Nos 16 Man Rank & File at Seme, Badagry, Lagos State (Lot C & D) | SEME | 2 | MESSRS DECA PROJECT CONSTRUCTION LIMITED | Residential |  | 2022-07-08 | - | - | - | Abandoned. The contractor should be written or invited to investigate the reason for not being on site
Zone A | Seme | Contract for the Renovation of Nigeria Customs Service Barracks at Seme, Badagry, Lagos State | SEME |  | MESSRS MAGNUM SYNERGY DYNAMIC INNOVATION LIMITED | Residential | - | - |  | 2023-03-23 | - | Abandoned
Zone A | Western Marine | Contract for the Demolition of Existing Dilapidated Structures and Construction of Standard Office Building at Western Marine , Ibafon, Lagos | WMC, Ibafon, Lagos | 1 | Messrs Joshuel Global Ventures | Administrative | 883473097.49 | 2024-12-01 | - | - |  | Work is currently ongoing on-site
Zone A | Western Marine | Contract for the construction of 2 nos 16 Man Rank and File | WMC, Ibafon, Lagos | 2 | Messrs Blissfred Constructi on Ltd | Residential | 854937854.8 | 2024-08-01 | - | - |  | One is currently ongoing while the other is awaiting demolition of the dilapidated office block
Zone A | Western Marine | Contract for the Supply and Installation of Solar Street Lights at Okokomaiko, Senior Officers’ Qtrs Maryland, Western Marine Ibafon, Ikorodu | WMC, Ibafon, Lagos |  | Messrs Emirate Builders Ltd |  | 93428260.22 | 2026-04-26 | - | -
Zone A | Zone A HQTRS | Contract for the Construction of Ultra-modern Customs Zonal Office and Sickbay at Warehouse Road, Apapa, Lagos | Apapa Lagos, Lagos State | 1 | Messrs Xmatrix 369 Limited | Administrative | 8488717479.19 | 2023-12-07 | - | - |  | Substructural works completed. The contractor should be invited to investigate the reason for abandonment
Zone A | Zone A HQTRS | Contract for the Demolition and Construction of 2 Blocks of 6 Storey 3 Bedroom Flats and 5 Blocks of 6 Storey 2 Bedroom Flats with Infrastructure Including Road Network, Carpark, Water Supply System, Fencing Modification and Gatehouse at the NCS owned land at Harvey Road, Yaba, Lagos State | Harvey Road Yaba, Lagos | 7 | Messrs JRB Construction Co Ltd | Residential | 6459754048 | 2023-01-05 | - | - |  | The contractor should be invited to investigate the reason for abandonment
Zone A | Zone A HQTRS | Construction Of FOU A Office Buildings / Nigeria Customs Service Training College | Iperu/Ilisan Road, Ogun State | 128 | CBC Global Civil & Building Construction Nigeria Ltd | Administrative & Residential | 73003871407.74 | 2023-01-11 | - | - |  | Work is ongoing on-site, however, the progress is behind schedule due various administrative delays
Zone A | Zone A HQTRS | Construction of 6 Blocks of 12 Nos 2 Bedroom Flats at Medical Road Barracks, Ikeja, Lagos | Medical Road, Ikeja Barrack, Lagos | 6 | Messrs Warams Services Ltd | Residential | 4976969281.82 | 2026-06-02 | - | - |  | Work is ongoing on-site. Substructural work is at completion stage
Zone A | Zone A HQTRS | Contract for the renovation and modification of 4 blocks of 3 and 2 bedroom flats including fence gatehouse reconstruction and landscaping at No 19,21,23 moshood Abiola cresent ikeja. | Abiola Crescent, Ikeja, Lagos | 4 | Messrs Totalmark Global Ltd | Residential | - | - | 6,99,665,377.10 | 15/1/2026 |  | Work is ongoing on-site
Zone A | Zone A HQTRS | Contract for renovation of 2Nos 30 man rank and file at Okokomaiko lagos | Okokomaiko, Lagos | 2 | Messrs Kingskid Concept Ltd | Residential | - | - | 923466668.7 | 2026-02-02 |  | Work is ongoing on-site
Zone A | Zone A HQTRS | Contract for the completion of the construction of 5 blocks of 10 N0s bedroom flats at marine beach barracks apapa | Marine Beach, Apapa, Lagos | 5 | Messrs Kadforex Integerated Service Ltd | Residential | 4226539288.41 | 20/1/2026 |  |  |  | Work is ongoing on-site
B | FCT | Construction of 32 blocks of two-bedroom apartments, a mosque, a chapel, and an Islamic school | FCT | 1 | Messrs. Warams Services Limited | - |  |  |  |  | Residential
Zone B | FCT | Construction of 15 blocks of three-bedroom apartments | FCT | 1 | Messrs. Ammsco Limited | [5 empty] | Residential
Zone B | FCT | Construction of the FCT Office | FCT | 1 | Messrs. Alternative Business Solution Limited | [5 empty] | Administrative
Zone B | FCT | Construction of two rank-and-file residential blocks | FCT | 4 | Messrs. Autonorths Limited
Zone B | FCT | Construction of the Officers' Mess | FCT | 1 | Messrs. Amal Engineering Services Limited
Zone B | FCT | Construction of the ant's Residence | FCT | 1 | Messrs. Grand Business Systems
Zone B | FCT | Construction of the shopping mall. |  |  | Messrs. Dirham Nigeria Limited
Zone B | FCT | Construction of the primary school |  |  | Messrs. Pride Rock
Zone B | FCT | Construction of maintenance facility, generator house, gatehouse, and perimeter fence. |  |  | Messrs. Kromches
Zone B | FCT | Construction and laying of the road network |  |  | Messrs. CBC Global
Zone B | FCT | Installation of the integrated sewage system |  |  | Messrs. Cavallini Construction Limited
Zone B | FCT | Management of borehole drilling and water tank installations |  |  | Messrs. Bran and Lugbe
Zone B | FCT | Supply and installation of electrical components, transformers, generators, solar street lights, and poles. |  |  | Messrs. Renecon, Messrs. Musty Global Power Company Limited, and Messrs. Urban Power Solutions
Zone B | Niger | Contract For the Completion of the Construction Of 2-Block Of 6 Units 2 Bedroom And 1-Block Of 6 Units 3 Bedroom Flat Behind Customs House Minna. | Behind Customs House Minna. | 1 | MESSRS ADKAY WORLDWIDE SERVICES LIMITED. | N207,325,808.28 | 24 FEB 26/ 11 AUG 26 |  |  | Ongoing | Administrative | Ongoing
Zone B | Niger | Contract For the Completion of the Construction Of 1. No 16 Man, Rank and File at Shango Minna. | Behind Customs House Minna. | 1 | MESSRS REFINED GOLDEN ABM NIGERIA LIMITED. | N239,803,820.30 | 26 MAR 26/ 05 NOV 26 |  |  | Ongoing | Administrative | Ongoing
Zone B | Niger | Drilling Of 89-Units Of Borehole and Construction Of 5000 Gallon Grp Overhead Tanks with Solar System (9-Units) | Various locations within the . | 1 | MESSRS CHEERYNA ENGINEERING SERVICES NIG. LTD. |  | 11 JUL 23/ 14 May 24 |  |  | Abandoned | Administrative | Abandoned
Zone B | Niger | Drilling Of Solar Borehole and Construction of Overhead Tank | Babanna Border Station | 1 | MESSRS COM ENGINEERING AND CONSTRUCTION | [5 empty] | Administrative | Abandoned (Contractor did not report to the )
Zone B | Niger | Supply And Installation Of 1 No 60kva Generating Set, at Customs House Minna. | Customs House Minna. | 1 | MESSRS FIRST BROAD INTERNATIONAL LIMITED |  | 2024-08-26 00:00:00 |  |  |  | Administrative | Abandoned
Zone B | Niger | Contract for the Construction of Perimeter Fence And Gate House For The Ongoing Construction of Clinic at Customs House Minna, Niger State. (Job Order). | Customs Barracks, behind customs house Minna | 1 | MESSRS ADAP CONSULT LIMITED | N14,916,360.30 | 30 Sep 24/ 20 Jan 25 |  |  | Completed | Administrative | Completed
Zone B | Niger | Contract for the additional items in the recently completed clinic, Customs House Minna, Niger/Kogi . (Job Order) | Customs Barracks, behind customs house Minna | 1 | MESSRS PROJECT DEVELOPMENT AND INVESTMENT CO. LTD | N9,876,025.00 | 26 Mar 25/ 03 Apr 25 |  |  | Completed | Administrative | Completed
Zone D | Plateau/Nassarawa/Benue | 2nos 16 man rank and file | Miango | 2 | Messrs Mosbat Consult & Associate Ltd. | 445847207.49 | 2025 |  |  | ongoing | Residential | Satisfactory
Zone D | Plateau/Nassarawa/Benue | 2nos 30 man rank and file Lot A&B | Lafia road Makurdi | 2 | Messrs Sanrahz Global Links Nigeria Ltd |  |  | 498,643,108,48 | 2025 | Ongoing | Residential | Satisfactory
Zone D | Plateau/Nassarawa/Benue | Clinic | Lafia road Makurdi | 1 | Messrs Halashela Global Resources Ltd |  | 2025 |  |  | ongoing | Administrative | Satisfactory
Zone D | Plateau/Nassarawa/Benue | Officers mess | Lafia road Makurdi | 1 | Messrs Yannsa Contractors Nig. Ltd | 282334280.04 | 2025 |  |  | ongoing | Administrative | Satisfactory
Zone D | Borno/Yobe | Contract for the demolition and reconstruction of old administrative block at customs house Maiduguri | Maiduguri | 1 | Messrs Gatedoors resources limited | 488,335,260.82 | 23/12/25 | -- | -- | Ongoing | Administrative | New Project
Zone D | Borno/Yobe | Contract for the reconstruction of perimeter fence and landscaping at junior officers barracks Maiduguri | Maiduguri | -- | Messrs ahram global resources limited | 119,520,545.64 | 23/12/25 | -- | -- | -- | Residential | Newly Completed
Zone D | Borno/Yobe | Contract for the supply and installation of 300KVA transformer and associated electrical components at customs house Maiduguri | Maiduguri | 1 | Messrs Dym Tech Nig. Limited. | 39,760,195.42 | 30/12/25 | -- | -- | Ongoing | -- | Ongoing Installation Project
Zone D | Borno/Yobe | Contract for the reconstruction of perimeter fence at borno/yobe command | Maiduguri | -- | Messrs Rock Bran Nigeria limited | 15,952,322.75 | 09/02/26 | -- | -- | -- | Administrative | Newly Completely
Zone D | Borno/Yobe | Contract for the reconstruction of perimeter fence, renovation of 8 rooms & parlour of 16-man rank and file and landscaping at senior officers barracks ruwan zafi maiduguri | Maiduguri | -- | Messrs JJ & H Nigeria limited | 449,378,042.43 | 23/12/25 | -- | -- | Ongoing | Residential | Ongoing New Construction
Zone D | Borno/Yobe | Contract additional landscaping and interlocking at customs house Maiduguri. | Maiduguri | -- |  | 55,196,077.32 |  | -- | -- | Ongoing | Administrative | Ongoing Project
Zone D | Borno/Yobe | Contract for completion of the construction of 30 man rank and file at Geidam, yobe state | Geidam | 1 |  | 612,258,584.51 |  | -- | -- | Ongoing | Residential | Ongoing Construction Project
Zone D | Borno/Yobe | Contract for renovation of mechanic workshop and transit camp at customs house, Maiduguri. | Maiduguri | -- |  | -- | -- | 218,159,342.02 |  | Ongoing | Administrative | Ongoing Renovation Project
Zone D | Borno/Yobe | Contract for rehabilitation of primary school at sakwa/hema (CSR), Borno | Sakwa/hema | 1 |  | -- | -- | 129,532,317.77 |  | Ongoing | Administrative | Ongoing Renovation Project
Zone D | Borno/Yobe | Contract for renovation of senior and junior officers mess behind customs house Maiduguri. | Maiduguri | 2 |  | -- | -- | 179,886,758.16 |  | Ongoing | Residential | Ongoing Renovation Project